## Sheet1
Projects Mamagement and Strategic Planning Unit of NIHR
Executive Plan for designing a strategic plan of NIHR
The operational plan is designed to meet the strategic plan to accomplish the objectives of the organizations for 2016
Plan Code : 1 |  |  |  | Section name: planning |  |  | Administrator name: Zain Al-Abidin Jasim Kadhim
Objectives | Elements | Required activities | Activties implementation mechanisms | impact |  | The time period | Measurement of success indication | Risk/alternatives | Monitoring and Evaluation | Nots
|  |  |  | Quantitative | Qualitative impact
first phase (preface): to create a successful strategic plan for 2016 to National Institute for Human Rights
| Preparation of plan | Write a report and submit it to the relevant authorities | Sending the reports to several stakeholders via e-mails and websites of the orgnization | .sending the report to (100) local and regional and international orgnizations | . Informing the stakeholders about the staratejic plan of the orgnization | 1/1/2016 _ 30/3/2016 | Confirmation of receipt and remarks (if any) | firmation of receipt | monitoring and assessment of all activities by the internal and external specified team
| . The Organization is preparing plans for future for activities and services and programmes. | . To provide an annual report containing its plans for next year and is distributed To the general assembely and the concerned parties. the Organization distributing plan on the staff of the organization. - the Organization distributing To the members of the Managment Council and discussed during the Board meeting. the Organization distributing annual plans. | Sending the activity to several stakeholder via e-mail | . Send the activity to ( organizations and institutions ) of relevant local, regional, and international. | . informing stakeholders of the local, regional, and international organizations. And stakeholders with mutueal goals by the activity. | Start:.1/1/2016 end implementation:-31/12/2016 | Confirm receipt of the activity by the receiver with feedback about it | . Change the methods and timing of activity | monitoring and assessment of all activities by the internal and external specified team
| The policies of the organization in the field of public relations | . The organization participates actively in regional federations, or as a member of the associations and networks. -The Organization created the networking and has the ability to maintain close relations with the community. -The organization is on constant and direct contact with other NGOs for the coordination and exchange of information. The Organization shares the work with other NGOs in the preparation of plans and identifies the roles of each. The Organization will share its(cash, human and visual)resources with organizations, association and regional, local, and international agencies - The Organization shares the meetings and activity implementation with other civil society organizations. | . Involve staff in a variety of exercises that are held by global and regional organizations in the field of public relations. -Networking relationships with the community to support their positions and promoting socially for objectives espoused by. | Involvement (10) members of staff of the organization in the trainings held by global and regional organizations in the field of public relations. | . Developing scientific and skillful capacities and abilities in the field public relations. | Start implementation:.1/1/2016 end implementation:-31/12/2016 | Doing media activities and systematic relations. members of staff of the Organization have the information and capacity for media and global relations. | . Open sessions with the capabilities of the organization. | monitoring and assessment of all activities by the internal and external specified team
1-1. | The numbers of staffs of the Institute for the year 2016 | Involve as many stakeholders of the expert and competent as possible in the activities of the Institute, 2016 | Engaging the stakeholders in the actvities of the organization for the year 2016 | 60 of both genders | Specialties (IT_ management _ accounting _ training ) | 1/1/2016- 31-12-2016 | 31-12-2016 | in case there was no work affilation applications, then the methodoligy regarding the mechanism of work will be changed and diagnosing gaps and failures. | monitoring and assessment of all activities by the internal and external specified team | Publishing the join request to the institute by media in addition to the e-mail of the organizations and its website
1-1. | The rules of procedure of the Institute | Review its articles in the annual general and .administrative boards meeting | Annual meetings of the general and administrative boards | Holding an annual meeting for the general and administrative boards in 2016 | Development by modify, delete, and add articles and items for the rules of procedure | 31\1\2016 until 1\2\2016 | 31-4-2016 | . Holding a meeting, and developing the rules of procedure in accordance with the target group community requirements. | monitoring and evaluation of all activities by the internal and external team prepared for those activites. | Postpone the meeting for a period not exceeding 45 days
| The rules of procedure of the Institute | General assembly shall hold one meeting nnually at least . The Board shall hold one meeting at least once a month. -Preparation and distribution of the agenda of the meetings of the Board before the date of holding. | the Board shall provide an opportunity for employees and members of the General body of opinion about decisions and the Council agenda. -Prepare and print records of Board meetings regularly and the Board calls its working members and General body To attend Board meetings and Committee meetings. -Document records of the meetings of the Board and the General body. | 2016 Holding at least one annual meeting for the year 2016 Holding administration board meetings at least once monthly for the year 2016 | -the Organization has a list of written rules of procedure. -distribution the list To all the members of the Board. -the Organization defines its internal rules for the members of the General body. | Holding a meeting for the general board, and not to exceed the date of 29/2/2016, and the meeting of the administrative board throughout a period that will not exceed the end of each month. | . Holding the meetings in the specific time and place. Developing the rules of procedure in line with the achieved objectives of the activities of the organization. | . Postponing the time and place of activity to ensure the completion of holding. | اonitoring and assessment of all activities by the internal and external team prepared for those activities.
1-2. | . Vision, mission, and values of the Institute. | Review the visions in the annual meeting of the general Body. | Annual meeting and practice to achieve the vision | Holding an annual meeting for the year 2016 | Developing the vision, mission and values of the Institute. | 2016-01-01 | 31-4-2016 | Holding a meeting, and developing the vision, mission and values of the Institute by what serves the interests of the stakeholders | monitoring and assessment of all activities by the internal and external team prepared for those activities. | Postpone the meeting for a period not exceeding 30 days
| . Vision, mission and values of the Institute. | . The mission statement is reviewed on the administrative Board and ratified by vote. -Mission statement is logged in the publications of the Organization such as its annual report. | . the Organization conducts an annual survey on member satisfaction and view survey results on members classified according To social type. - the Organization conducts an annual survey on member satisfaction and view results of the survey To the members. the Organization regularly conducts an annual survey on member satisfaction on its work. -the Organization is conducting research on member satisfaction on its activities during the past period. | Holding a meeting regularly and at least once a year to the general body. Holding a meeting regularly and at least once a month to the administrative body. | Commitment by the social balance in the Board and its committees. Youth representation at adequate between the members of the general body and the Board | From 1\1\ 2016 to 12\31\ 2016 | . The Organization has a written mission statement. -Publication of the annual report of the organization. Holding a meeting to develop the vision and the mission, with what commensurate with serving the public interest. | Holding a meeting, and developing the vision, mission and values of the Institute by what serves the interests of the stakeholders | monitoring and assessment of all activities by the internal and external team prepared for those activities.
1-3. | (SWOT) Analysis of the internal and external environment of the Organization for the study of the current situation with the (SWOT) method. | Review articles in the meetings of the Administrative Board | Regular meetings | Holding (5) regular meetings for 2016 | (SWOT) Developing the current situation of the orgnization by applying (SWOT) method | 2016-01-01 | 31-5-2016 | (SWOT) Holding a meeting, and developing the current situation of the Organization using the method of (SWOT) | monitoring and assessment of all activities by the internal and external team prepared for those activities. | Holding frequent meetings
| )Analysis of the internal and external environment of the Organization for the study of the current situation by using (SWOT) method for the following topics (performance of the Organization – Administrative Board - activities quality - organizational structure – biography of the Organization – decision-making mechanism - means of communication with others - public relations and administrative systems and informatics - monitoring and evaluation system – experiences - donor relations -methods of service delivery - human resources -political, economic and social conditions of geographic surrounding – internal legislations and laws – finance – partnerships - partnerships and community and stakeholders - and other related topics) | .Revision and distribution of reports on its work To members of the General authority and members of the community. -Preparation and presentation of reports. -an annual survey on the performance of the Organization and member satisfaction. -Following methods of transparency in decision making process. | . Through a single annual meeting at least annually for members of the public authority. -By holding a regular meeting every month for at least once for the members of the administrative authority. | . - Holding an annual meeting at least once for the members of the general authority. - Holding a monthly meeting at least once for the members of the administrative authority. | . Review the strengths of the Institute for the purpose of development - Review the weaknesses and diagnose them for the purpose of finding ways to deal with them to avoid their recurrence. | . From 1\1\ 2016 to 31\12\ 2016 | (SWOT). Increase in number of members of the general authority of the Institute. -Holding annual and monthly meetings. -Taking into account the views of the grassroots. - Developing of the Organization's performance through performance review. -Using (SWOT) method. | . Changing schedules and venues of meetings holding and the applied methodology. | monitoring and assessment of all activities by the internal and external team prepared for those activities.
1-4. | The policies of the Institute in the areas of training | Revision of annual strategic training plans | Involve the staff in various trainings that are organized by local, regional and international organizations | . Involvement 28 of staffs of the Organization in trainings related to the Institute's objectives. | Increase the skills and knowledge of staff regarding matters related to their tasks. | 2016-01-01 | 31-12-2016 | training by the staff | monitoring and assessment of all activities by the internal and external team prepared for those activities.